## CPQ Rollout Batam PP (hidden)
|  |  | High | Planned
|  |  | Medium | WIP
|  |  | Low | WIP 25%
WIP 50%
WIP 75%
WIP 90%
Completed
Interplex CPQ Harmonization and Rollouts
with integration
|  | KPI |  |  | July |  |  |  | Aug |  |  |  | Sept
Task | Game Plan | $ 'M | Priority | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Owner | Dependency | Comments
1 | Batam - AEB-HDD, APB, APCB Rollout |  |  | WIP 25% | [12 empty] | Joanne/ Jiawei | InMind
1.1 | Kick Off and Requirements Confirmation |  |  | Completed | 2 | [11 empty] | Joanne/ Jiawei | InMind
1.2 | User Requirement Gathering |  |  | Completed | 2 | [11 empty] | Joanne/ Jiawei | InMind
1.3 | Fit & Gap analysis |  |  | Completed | 5 | [11 empty] | InMind
1.4 | Requirements Sign Off |  |  |  |  | 10 |  |  | 7 |  |  |  | 7 | [5 empty] | Pending Acknowledgement. Key Users fromo each plant to sign off the requirement document.
1.5 | Development |  |  | WIP |  |  | 19 |  |  |  | 21 |  |  |  | 21 |  | InMind | Champions | Initial Assumption to start on 19th July, but no outcome till now.
1.6 | User Training (2 days) |  |  | Planned |  |  |  | 24 |  |  |  | 24 |  |  |  |  | InMind (Alex) | Champions | 1 day training - APCB & AEB-HPES, 1 day training for APB
1.7 | UAT and sign off |  |  | Planned | [5 empty] | 16 |  |  |  | 14 |  |  | Champions | Champions | assuming 1x revision
1.8 | Deployment to production system |  |  | Planned | [6 empty] | 23 |  |  |  | 23 |  | InMind | InMind
1.9 | Go live |  |  | Planned | [7 empty] | 26 |  |  |  | 24
Completed items
Training
Introduction of CPQ to Costing Manager
Scheduled
Completed
Delayed

## Legal Repository SPOnline
|  |  | High | Planned
|  |  | Medium | WIP
|  |  | Low | WIP 25%
WIP 50%
WIP 75%
WIP 90%
Completed
Interplex Legal Repository
[6 empty] | Scheduled |  |  |  |  | Completed |  |  |  | Delayed
|  | KPI |  |  | July |  |  |  | Aug |  |  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Jan |  |  |  | Feb |  |  |  | March
Task | Game Plan | $ 'M | Priority | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Owner | Dependency | Comments
1 | Legal Repository Site |  |  | Planned
1.1 | Site Provision |  |  | Completed |  |  | 19
1.2 | Data Structure |  |  | Completed | [6 empty] | 20
1.3 | Upgrade Meta Data Forms |  |  | WIP | [7 empty] | 28
1.4 | Workflow |  |  | Planned | [9 empty] | 11
1.5 | Advance Search |  |  | Planned | [9 empty] | 14
1.6 | HomePage |  |  | Planned | [10 empty] | 16
1.7 | User Testing and Bug Fixes |  |  | Planned | [11 empty] | 19
1.8 | User Training |  |  | Planned | [13 empty] | 14
1.9 | Sign Off |  |  | Planned | [16 empty] | 4
1.1 | Go Live |  |  | Planned | [16 empty] | 6
Completed items
Training
| Introduction of CPQ to Costing Manager | [35 empty] | Jiawei | InMind, Manoj | Basic introduction Completed.
Scheduled
Completed
Delayed

## CPQ Rollout Overall (hidden)
|  |  | High | Planned
|  |  | Medium | WIP
|  |  | Low | WIP 25%
WIP 50%
WIP 75%
WIP 90%
Completed
Interplex CPQ Harmonization and Rollouts
with integration
[6 empty] | Scheduled |  |  |  |  | Completed |  |  |  | Delayed
|  | KPI |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June
Task | Game Plan | $ 'M | Priority | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Comments
1 | CPQ Upgrade | [14 empty] | 31 |  | 10 | [5 empty] | 29 | [12 empty] | 1902, 1904 upgrade completed early
2 | Harmonization of CPQ | [25 empty] | 23 | [9 empty] | 1. Delay due to critical bug and underestimated effort. 2. Critical bug resolution took longer than expected. 3. Additional tasks are added due to unharmonized profit price calculation
2.1 | Profit Calculation Signoff | [26 empty] | 26 | [8 empty] | Additional requirements
2.2 | Calculation Implementation | [29 empty] | 24 | [5 empty] | Additional requirements, includes implementation and one round of SIT by champions
3 | Enhancement Requests | [24 empty] | 12 | [10 empty] | Enhancements Completed except for SAP integration, Snowballed due to harmonization
4 | UAT Sign Off* | [20 empty] | 15 | [9 empty] | 28 |  |  |  |  | Prerequisite to last task, delayed due to above activities. One round of full testing.
5 | Training of Upgraded CPQ and UAT of Harmonized Enhancement | [32 empty] | 10 |  |  | Delayed due to uncompleted tasks above.

## Sheet1
S/No | Milestone Description | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01
1 | CPQ Upgrade
2 | Harmonization of CPQ
2.1 | Profit Calculation Signoff
2.2 | Calculation Implementation
3 | Enhancement Requests
4 | UAT Sign Off*
5 | Training of Upgraded CPQ and UAT of Harmonized Enhancement
|  | 2018-11-01: KPI; 2019-02-01: Nov; 2019-06-01: Dec |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  | June
Task | Game Plan | $ 'M | Priority | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | CPQ Upgrade | [14 empty] | 31 |  | 10 | [5 empty] | 29 | bar: 2019-02-01 to 2019-07-01
2 | Harmonization of CPQ | [25 empty] | 23 | bar: 2019-06-01 to 2019-07-01
2.1 | Profit Calculation Signoff | [26 empty] | 26
2.2 | Calculation Implementation | [29 empty] | 24
3 | Enhancement Requests | [24 empty] | 12 | bar: 2019-06-01 to 2019-07-01
4 | UAT Sign Off* | [20 empty] | 15 | [9 empty] | 28
5 | Training of Upgraded CPQ and UAT of Harmonized Enhancement | [32 empty] | 10

## Sheet2
S/No | Milestone Description | Status | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01
1 | CPQ Upgrade | Complete
2 | Harmonization and Enhancements | Complete
2.1 | UAT1 | Complete
2.2 | UAT2 | Complete
2.3 | UAT3 | Complete
3 | Final Training for Upgraded and Harmonized CPQ | Complete
4 | Final User Acceptance Test UAT Sign Off* | In Progress
5 | Deployment and support | Planned
6 | Batam Rollout | In Progress

## HRIS Tasks (hidden)
Action Item Register :
Planned
25% WIP
50% WIP
75% WIP
| SORTED BY PRIORITY AND BY DUE DATE | [11 empty] | Completed
0
| S/N | Portfolio Region | Category | Priority | Due Date | Issue | Owner | Champion | Resolution | Activities Completed Last Week | Activities Completed Current Week | Closure Date | Status | Risk / Issues / Comments
| 1 | Corporate Finance | Recruitment | Very High | 2018-10-30 | Lack of Expertise in Interplex to lead and guide sites and region. | George | Jocelin | Have shortlisted candidate with rich exerience in cost accounting in manufacturing. | Offer has been accepted by Candidate |  | 2018-11-07 | 75% WIP | Candidate will join Interplex on 7th of Nov.
2
3
4
5
6
7
8
Lease | 9
10
11
12
13
14
15
16
17
18
Governance | 19
20
IT | 21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36

## JEC Deliverables (hidden)
Planned
WIP
WIP 25%
WIP 50%
WIP 75%
WIP 90%
Completed
| PSB Academy | [25 empty] | EduCo Institutionalized Field Marketing
|  |  |  | Scheduled | [6 empty] | Completed |  |  |  |  | Delayed
|  | KPI |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr
| Functional | $ 'M | Status | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | Baring | PSB | Comments
Game Plan
1 | Overall priorities – 5 point plan for Senior Management
1.1 | Sales and Marketing Revamp - Re-organization to split out Domestic and International - Targeted initiatives to reduce leakages out of sales ‘funnel’ |  | Completed | [20 empty] | Manish | Viva/ Derrick | Re-organization completed. Initiatives being developed and implemented at both overall level (e.g. call centre, walk-in team) and individual program level. To implement all initiatives by Feb Reported with BOD in March
1.2 | Improving productivity - Rigorous, weekly tracking of performance and issues - Freeze on new hires; conduct org diagnostics across all teams |  | WIP 90% | [20 empty] | Manish | Viva/ Derrick | Comprehensive weekly tracking and tight governance implemented Org diagnostics completed. To finalise with SMM
1.3 | Cost Optimisation - Full review of all cost items |  | WIP | [20 empty] | Manish | Viva/ Derrick | Cost items being reviewed in detail
1.4 | New Product Development - Introduce new products and develop pipeline - Finalise framework for new product launches |  | WIP | [20 empty] | Manish | Viva / Joao / Brian | New products identified and framework laucnhed - team currently actively sourcing for new partners and programs to begin negotiations. Ongoing
1.5 | Student Centricity - Culture change towards student centricity and driving WoM - Organization change in SSC, with new service policies |  | WIP | [20 empty] | Manish | Viva/ Derrick/ Vijyah | Revamp of Student Services and org restructure completed Org change underway
2 | Sales and Marketing
2.1 | Improve Progression rates - Finalise team structure issues - Improve tracking and visibility - Improve engagement through careers outreach |  | WIP 50% | [20 empty] | Manish | Julia | Team structure issues finalised Careers outreach planned Tracking solution being developed
2.2 | Country sales plans |  | Completed | [20 empty] | Manish | Daren | Plans finalised and resources in place. Commencing key activities (e.g. school partnerships, targeted activities for key agents)
2.3 | Revamp sales team structure and incentives; review targets |  | Completed | [20 empty] | Manish | Julia
2.4 | Resolve BEnvOSH articulation issue |  | WIP | [20 empty] | Manish | Julia/ Joao | Seeking alternative programs Additional DBA and LTU intakes to recover numbers
2.5 | Tighten brand messaging and created more targeted outreach |  | WIP | [20 empty] | Manish | Derrick | New proposal being tabled for discussion at TMM
3 | School Operations
3.1 | Further streamlining of operations - Redefine role of Program Execs - Streamlining of operations, systems and redundant processes |  | WIP | [20 empty] | Manish | Vincent | Review in Q1
4 | Academics
4.1 | Curriculum review under Academic Framework, to improve teaching and learning performance |  | WIP | [20 empty] | Manish | Joao
4.2 | New framework to manage ALs, to drive greater cost efficiency and improve duty of care |  | WIP 90% | [20 empty] | Manish | Joao | Phase 1 Plan developed, awaiting final approval
4.3 | Improve tracking of academic metrics |  | WIP 75% | [20 empty] | Manish | Joao | Initial metrics completed, to be refined over next 2 weeks
5 | IT
5.1 | E-Teams review and solution - finalise plan |  | WIP 75% | [20 empty] | Manish | Ben | Consultant creating final report
5.2 | Scheduling software - feasibility study |  | Completed | [20 empty] | Manish | Ben | Finalise study Full rollout by 31 July
6 | Campus
6.1 | New campus - develop detailed plan, involving all stakeholders |  | WIP 50% | [20 empty] | Manish | Ben | Engaged staff to contribute ideas on cam
6.2 | New campus - shortlist systems and architect |  | WIP | [20 empty] | Manish | Ben
7 | HR
7.1 | Org diagnostic |  | WIP 50% | [20 empty] | Manish | Cecilia
7.2 | Improve staff engagement - ongoing |  | WIP | [20 empty] | Manish | Cecilia | Focused activities being conducted by department
8 | STA
8.1 | Implement overall student engagement plan, with student journey for international students |  | WIP 75% | [20 empty] | Manish | Vijyah | Plan developed, being refined Fully implemented by Q1
8.2 | Careers services enhancement - planning |  | Completed | [20 empty] | Manish | Vijyah | Enhanced career visits, workshops, networking events planned
9 | ODQA - Prepare for Edutrust Interim Audit |  | WIP | [20 empty] | Manish | Dominic | Internal review underway External consultant findings being implemented
10 | Corporate Strategy
| Support Vietnam integration and business planning |  | WIP | [20 empty] | Manish | Brian | On going support with Sales and Marketing as well as Operational issues
| Finalise 3-5 year product portfolio plans |  | WIP 90% | [20 empty] | Manish | Brian | Conducted gap analysis. Program and partner sourcing underway
11 | Finance - on-time closing of books (ongoing) |  | WIP | [20 empty] | Manish | Subbu